## R12.2 Issues Backlog
Id | Component | Module | Title | Priority | Status | Date Opened | Description | CMS Impact | Release Date
10559 | Patient Safety | Analysis and Reporting | AUR - Blank reports are displayed when generated for Rate tables when changed Display Options groupby to summary YH | 2-High | Open | 2023-04-06 14:16 | Blank reports are displayed when generated for Rate tables when changed Display Options groupby to summary YH. | No | TBD
10574 | Patient Safety | Antimicrobial Use | Group AR Option Incidence Reports - Cumulative Patient Days Not Displaying for All Facilities | 2-High | Open | 2023-04-17 12:44 | When running the Rate Table - Hospital-onset Positive Culture Incidence by Organism report with groupBy=cumulative, the denominator data (patient days) is not displaying for some facilities. | No | TBD
10607 | Patient Safety | Analysis and Reporting | A&R Plot displays incomplete time periods for SummaryYH and SummaryYr | 1-Urgent | Open | 2023-05-15 13:03 | Similar to the SAAR reports, the SAAR Plot reports should only display data for completed time periods. Currently, the SAAR Plot reports will display completed time periods for summaryYM and summaryYQ (e.g. not displaying data for 2023M05 or 2023Q2), but will display incomplete time periods for summaryYH and summaryYr (e.g. displaying data for 2023H1 and 2023 in May 2023). | No | TBD
10609 | Patient Safety | Analysis and Reporting | A&R Plot suppression issues | 1-Urgent | Open | 2023-05-15 16:19 | The SAAR reports and SAAR Plot reports should use the same suppression rules. Currently, the data in the SAAR Plot reports are sometimes suppressed when they are not suppressed in the SAAR reports. The SAAR reports should be the source of truth for what should and should not be suppressed. | No | TBD
10659 | Healthcare Personnel Safety | Analysis and Reporting | Issue with PctAllVacc variable in C19 pre-10.0 report | 1-Urgent | Open | 2023-06-24 | The PctAllVacc variable is not calculating after SurvWeekEnd of 08/08/2021. | No | TBD
10954 | Patient Safety | Antimicrobial Use | Intermittently receiving 504 Errors when sending AR/AU files via Direct | 2-High | Open | 2024-03-11 17:59 | Vendor has reported intermittently receiving 504 errors when sending files via Direct, which appears to have started occurring after the NHSN Cloud migration. | No | TBD