## Slide 1: NNDSS Modernization Initiative (NMI): Update on and Recent Lessons Learned from NMI Onboarding
May 16, 2017 Division of Health Informatics and Surveillance
Subscribe to monthly NMI Notes news updates at https://www.cdc.gov/nndss/trc/news/index.html!
Access the NNDSS Technical Resource Center at https://www.cdc.gov/nndss/trc/index.html!

## Slide 2: Agenda
Welcome
Announcement: Update on NMI Timeline
Update on and Recent Lessons Learned from NMI Onboarding
Hot Topics:
  Onboarding New Generic v2 Conditions
General Questions and Answers

## Slide 3: Announcement: Expected Timeline for NMI
Generic v2 and hepatitis migrate to Message Validation, Processing, and Provisioning System update (MVPSu) in late July 2017.
MVPSu ready to receive STD and congenital syphilis case notification messages in October 2017.
MVPSu ready to receive mumps and pertussis case notification messages in December 2017.
MVPSu ready to receive varicella case notification messages in February 2018.
Work continues on other message mapping guides (MMGs).
MMG team is creating re-usable data element blocks and templates, where possible.
MVPS team will update MVPS Dashboard in the future.

## Slide 4: Update on NMI Onboarding Activities and Process
Michele Hoover, MS
NMI State Implementation and Technical Assistance Team
Division of Health Informatics and Surveillance
Center for Surveillance, Epidemiology, and Laboratory Services
Centers for Disease Control and Prevention

## Slide 5: NMI Implementation Status May 2017
PR
Piloting Total of 6 (states)
Production Total of 10 (states)
Onboarding Total of 8 (states)
N=55 Jurisdictions
RI
AK
WA
OR
CA
MT
ID
WY
NE
NV
NM
TX
AR
TN
ME
VT
NY
FL
GA
AL
NC
VA
MI
PA
NJ
DE
NH
CT
MA
HI
AZ
LA
OK
KS
CO
UT
SD
MN
WI
IA
MO
IL
WV
MS
KY
OH
IN
MD
SC
ND
DC
New York City

## Slide 6: High Level NMI Onboarding Overview
Jurisdiction Test Environment
Jurisdiction Production Environment
MVPS Secure Onboarding Environment
MVPS Production Environment
Test Messages
Year-to-Date (YTD) Production Messages
Limited Production Messages
Step 1
Step 2
Step 3
Routine Production Messages
Step 4

## Slide 7: Step 1: Send Test Messages
Jurisdiction creates test messages based on the test case scenario spreadsheet provided by CDC.
  Ensures the jurisdiction’s system can generate and populate messages with the correct content
Jurisdiction sends test messages from their test environment to the MVPS onboarding environment.
CDC compares every data element in the message with the information provided in the test case scenario to validate content and structure.
Jurisdiction Test Environment
MVPS Secure Onboarding Environment
Test Messages

## Slide 8: Step 2: Send Limited Production Messages
Jurisdiction sends a limited set of production messages (10 for each MMG) from the jurisdiction production environment to the MVPS onboarding environment.
  Ensures no problems emerge due to move from test environment to production environment
CDC compares each data element in the message to the appropriate MMG.
Jurisdiction Production Environment
MVPS Secure Onboarding Environment
Limited Production Messages
MVPS onboarding environment has the same security features as MVPS production environment.

## Slide 9: Step 3: Send Production YTD Messages
Jurisdiction sends their production YTD messages to the MVPS production environment.
MVPS assesses the messages for errors and warnings that would prevent the message from being accepted.
Once all critical issues with the YTD messages are addressed, the jurisdiction will be approved for production and will continue transmitting any new case notifications to MVPS.
  The jurisdiction may be approved to go into production with contingencies.
Jurisdiction Production Environment
MVPS Production Environment
YTD Production Messages

## Slide 10: Step 4: Routine Production Message Transmission
Once the jurisdiction is approved to cutover to production, the jurisdiction will cutoff transmission from their legacy system.
The jurisdiction will continue sending any new case notification messages to MVPS.
Jurisdiction Production Environment
MVPS Production Environment
Routine Production Messages

## Slide 11: Lessons Learned from Issues Identified in the Data During NMI Onboarding
Michele Hoover, MS
NMI State Implementation and Technical Assistance Team
Division of Health Informatics and Surveillance
Center for Surveillance, Epidemiology, and Laboratory Services
Centers for Disease Control and Prevention

## Slide 12: Issues Identified During NMI Onboarding
Date and time for submission
  Use a 24-hour clock in all messages.
  Ensure that date first submitted to CDC (OBR-7) is consistent among cases.
Event codes
  Reclassify event codes to current codes.
  Exclude conditions that are no longer reportable.
Repeating Blocks
  Provide a unique combination of the data element identifier (OBX-3) and the observation sub ID (OBX-4).
Notes: TA

## Slide 13: Some Issues Do Not Prevent Going into Production
Counties within the state are missing.
Date of birth entry is invalid or missing.
Race and ethnicity entry is invalid.
Illness onset date is populated with date submitted to CDC.
Admission date is not provided in a hospitalization case.
Notes: TA

## Slide 14: Hot Topic: Onboarding New Generic v2 Conditions
Michele Hoover, MS
NMI State Implementation and Technical Assistance Team
Division of Health Informatics and Surveillance
Center for Surveillance, Epidemiology, and Laboratory Services
Centers for Disease Control and Prevention

## Slide 15: New Conditions for Generic v2 Only: Nationally Notifiable Conditions
The 2017 NNDSS Event Code List and Conditions to Use Generic v2-only List were updated to include:
  Cyclosporiasis (event code 11575),
  Trichinellosis (event code 10270), and
  Malaria (event code 10130).
    States must continue to send malaria case reports to the National Malaria Surveillance System until they have onboarded the malaria HL7 MMG.
Reminder: All jurisdiction-reportable conditions for each MMG are expected to be onboarded at the same time.

## Slide 16: New Conditions for Generic v2 Only: Standardized Criteria for Case Identification and Classification
The 2017 NNDSS Event Code List and case definitions have been updated to include the following:
  Acanthamoeba disease–excluding keratitis (event code 50225)
  Balamuthia mandrillaris disease (event code 50226)
  Naegleria fowleri causing Primary Amebic Meningoencephalitis (event code 50227)
These conditions are not Nationally Notifiable Conditions.
If jurisdictions collect data on these conditions, the CDC program would like to receive notifications using the Generic v2 Message Mapping Guide. Legacy formats will not be accepted.

## Slide 17: Process for Onboarding Newly Added Generic v2 Conditions Once Jurisdiction is in Production
Send email to EDX@cdc.gov with conditions to be onboarded.
CDC Onboarding team with update existing information to include the new conditions.
CDC Onboarding team will send an approval email to the jurisdiction.
State is onboarded and starts routine transmission.

## Slide 18: Upcoming eSHARE Webinars
June 20:
  NNDSS-Related Highlights from the 2017 Council of State and Territorial Epidemiologists Annual Meeting
July 18:
  Introduction of Industry and Occupational Template and Demonstration of National Institute for Occupational Safety and Health Industry and Occupation Computerized Coding System
August 15
  Panel Presentation of States Onboarded to MVPS to Discuss Barriers, Challenges, and Lessons Learned.

## Slide 19: Questions and Answers

## Slide 20: Additional Questions?
Subscribe to monthly NMI Notes news updates at https://www.cdc.gov/nndss/trc/news/index.html!
Access the NNDSS Technical Resource Center at https://www.cdc.gov/nndss/trc/index.html!
Request NMI technical assistance or onboarding at
edx@cdc.gov!
Next NMI eSHARE is June 20, 2017–details at https://www.cdc.gov/nndss/trc/onboarding/eshare.html!